## Sheet2
Team 197 Sprint 2 Plan
Owner: Shiqing Jing Member: Mouwu Lin, Shiqing Jing, Yadi Yang
Feature | Task | Responsor | Estimated Time(Unit: hour) | Actual Time(Unit: hour) | Description | Notes | Process
Static Template | Course list page | Shiqing Jing | 3 |  | Including course management, achieve management, plan management, create resume page and so on.
| Course management page | Mouwu Lin | 3
| Achievement management page | Yadi Yang | 2
| Plan management page | Shiqing Jing | 2
Design Model and Form | Course data | Shiqing Jing | 3 |  | Design all the relevant models and forms.
| Achievement data | Mouwu Lin | 2
| Plan data | Yadi Yang | 1
Design Urls | Design Urls for sprint 2 | Mouwu Lin | 0.5 |  | Design the Urls relvant to the functions in sprint 2.
Create Profile Function | Extract data from file | Shiqing Jing | 5 |  | Users can also upload their resume. After uploading, extracting data from pdf or word files.
| Load data | Shiqing Jing | 2
Course Management Function | Course data retrieval | Yadi Yang | 4 |  | Logged-in user could see the courses that recommend to them. They can save some course to their collection and manage those course. They can also view the current course list they can taking.
| Course data transfer and load | Yadi Yang | 4
| Course list update | Yadi Yang | 4
Achievement Management Function | Achievement definition | Mouwu Lin | 4 |  | Logged-in user could review their achievements in achievement manage page. They could view what courses they have finished and the accourding grade or certification.
| Achievement certificate and load | Mouwu Lin | 4
Plan Management Function | Plan data definition | Yadi Yang | 3 |  | Logged-in user could create their study plan including the course they plan to take, the expected complete time for the course. They can make several plans, for instance, weekly, monthly, yearly. Users can set their plans private or public.
| Schedule creation | Shiqing Jing | 5
| Course page redirection | Mouwu Lin | 3
Search Function | Search implementation | Mouwu Lin | 4 |  | The logged-in users can search for courses that they are interested in. They can also search for their plans, their profiles or other users profiles.
| Searching scope definition | Shiqing Jing | 2
| Return list display | Yadi Yang | 1
Test & Debug | Sprint 2 | Shiqing Jing, Mouwu Lin, Yadi Yang | 12 |  | Test all the functions and debug, and refractor the different function units for inneraction.
|  | Total time | 73.5