## Sheet2
Team 197 Sprint 3 Plan
Owner: Shiqing Jing Member: Mouwu Lin, Shiqing Jing, Yadi Yang
Feature | Task | Responsor | Estimated Time(Unit: hour) | Actual Time(Unit: hour) | Description | Notes | Process
Course Recommend System | Personalized Recommend | Shiqing Jing | 8 |  | Personalized recommendation based users' information on linkedin, their resume on our website and the resume they upload. We also recommend them some popular courses and courses other user takes who share similar skills
| Popular course recommendation | Mouwu Lin | 3
| Collaborative Filtering recommendation | Yadi Yang | 8
Design Urls | Design Urls for sprint 3 | Mouwu Lin | 0.5 |  | Design the Urls relvant to the functions in sprint 2.
Improve UI | Improve the layout | Yadi Yang | 3 |  | Improve the layout of the web page. Make the page more interative by add some Jquery features.
| Add some jquery features | Shiqing Jing | 4
Text Analysis | Add upload resume function | Yadi Yang | 2 |  | Allow users to upload their resume to the web page. Analysis their resume and retrieve keywords such as skill and experience for recommendation.
| analysis the text from the resume | Mouwu Lin | 8
Deploy to Heroku | Deploy the web app the heroku | Shiqing Jing | 6 |  | Deploy the web app to heroku. Store the static files and media file in AWS.
User Usability | Invite different users to use and offer feedback. | Mouwu Lin | 4 |  | Improve our web app based on the users' feedback
|  | Shiqing Jing | 4
| Improve based on their feedback | Yadi Yang | 4
Test & Debug | Sprint 2 | Shiqing Jing, Mouwu Lin, Yadi Yang | 15 |  | Test all the functions and debug, and refractor the different function units for inneraction.
|  | Total time | 69.5